## Project Overview
ROBUST OPTIMISATION – Infrastructure Scheduling under Traffic & Operational Uncertainty
Project: Urban Road Reconstruction – Sector 7 Arterial Corridor ¦ Location: Mid-size US city ¦ Duration: 8 Weeks (2 Months)
KEY PROJECT ASSUMPTIONS & UNCERTAINTY PARAMETERS
PROJECT PARAMETERS |  | UNCERTAINTY PARAMETERS
Start Date | 03-Mar-2025 | Traffic Delay Multiplier (peak) | 1.4 – 1.8×
End Date (planned) | 26-Apr-2025 | Traffic Delay Multiplier (off-peak) | 1.0 – 1.2×
Working Days | 40 | Task Duration Variance (σ) | ±15%
Working Hours/Day | 10 hrs (07:00–17:00) | Resource Availability Uncertainty | ±10%
Project Budget | 4250000 | Material Delivery Delay (prob.) | 25% chance / delivery
Contingency (10%) | 425000 | Weather Event Probability | 8% / week
Total Corridor Length | 2.4 km | Equipment Breakdown Probability | 5% / machine-day
Lanes Affected | 2 of 4 lanes | Cost Overrun per Delay Day | $8,500 – $12,000
Peak Traffic Vol. | 3,200 veh/hr | Monte Carlo Iterations (planned) | 10000

## WBS – Task Schedule
WORK BREAKDOWN STRUCTURE – Task Schedule with Planned vs Actual Tracking
Task ID | WBS Level | Task Name | Predecessor | Resource Type | Crew Size | Planned Start | Planned End | Planned Duration (days) | Actual Start | Actual End | Actual Duration (days) | Delay (days) | Delay Cause | Traffic Impact (H/M/L) | Planned Cost ($)
T01 | 1 | Site Mobilisation & Setup | – | General Labour | 8 | 03-Mar-2025 | 05-Mar-2025 | 3 | 03-Mar-2025 | 05-Mar-2025 | 3 | 0 | – | Low | 15600
T02 | 2 | Utility Survey & Marking | T01 | Survey Team | 4 | 06-Mar-2025 | 07-Mar-2025 | 2 | 06-Mar-2025 | 10-Mar-2025 | 3 | 1 | Traffic delay | Medium | 6800
T03 | 2.1 | Utility Relocation – Gas | T02 | Specialist Crew | 6 | 10-Mar-2025 | 14-Mar-2025 | 5 | 10-Mar-2025 | 18-Mar-2025 | 7 | 2 | Material delivery | High | 36000
T04 | 2.2 | Utility Relocation – Fibre | T02 | Specialist Crew | 5 | 10-Mar-2025 | 13-Mar-2025 | 4 | 10-Mar-2025 | 13-Mar-2025 | 4 | 0 | – | Medium | 24000
T05 | 3 | Traffic Diversion Setup | T01 | Traffic Mgmt | 6 | 06-Mar-2025 | 07-Mar-2025 | 2 | 06-Mar-2025 | 10-Mar-2025 | 3 | 1 | Permit delay | High | 9000
T06 | 3.1 | Lane Closure – Phase 1 | T05 | Traffic Mgmt | 4 | 10-Mar-2025 | 21-Mar-2025 | 10 | 10-Mar-2025 | 26-Mar-2025 | 13 | 3 | Traffic peak conflict | High | 30000
T07 | 4 | Pavement Milling – Seg A | T06 | Heavy Equipment | 5 | 13-Mar-2025 | 18-Mar-2025 | 4 | 13-Mar-2025 | 19-Mar-2025 | 5 | 1 | Equipment breakdown | High | 48000
T08 | 4.1 | Pavement Milling – Seg B | T07 | Heavy Equipment | 5 | 19-Mar-2025 | 24-Mar-2025 | 4 | 19-Mar-2025 | 24-Mar-2025 | 4 | 0 | – | High | 48000
T09 | 4.2 | Pavement Milling – Seg C | T08 | Heavy Equipment | 5 | 25-Mar-2025 | 28-Mar-2025 | 4 | 25-Mar-2025 | 01-Apr-2025 | 6 | 2 | Weather event | Medium | 48000
T10 | 5 | Sub-base Preparation – Seg A | T07 | Earthworks Crew | 7 | 19-Mar-2025 | 25-Mar-2025 | 5 | 19-Mar-2025 | 26-Mar-2025 | 6 | 1 | Traffic delay | Medium | 31500
T11 | 5.1 | Sub-base Preparation – Seg B | T10 | Earthworks Crew | 7 | 26-Mar-2025 | 01-Apr-2025 | 5 | 26-Mar-2025 | 01-Apr-2025 | 5 | 0 | – | Medium | 31500
T12 | 5.2 | Sub-base Preparation – Seg C | T11 | Earthworks Crew | 7 | 02-Apr-2025 | 08-Apr-2025 | 5 | 02-Apr-2025 | 10-Apr-2025 | 7 | 2 | Material delivery | Low | 31500
T13 | 6 | Drainage Installation – Seg A | T10 | Specialist Crew | 5 | 26-Mar-2025 | 02-Apr-2025 | 6 | 26-Mar-2025 | 03-Apr-2025 | 7 | 1 | Traffic conflict | High | 36000
T14 | 6.1 | Drainage Installation – Seg B | T13 | Specialist Crew | 5 | 03-Apr-2025 | 10-Apr-2025 | 6 | 03-Apr-2025 | 10-Apr-2025 | 6 | 0 | – | Medium | 36000
T15 | 6.2 | Drainage Installation – Seg C | T14 | Specialist Crew | 5 | 11-Apr-2025 | 17-Apr-2025 | 5 | 11-Apr-2025 | 22-Apr-2025 | 8 | 3 | Equipment breakdown | Medium | 30000
T16 | 7 | Base Course Laying – Seg A | T13 | Paving Crew | 8 | 03-Apr-2025 | 08-Apr-2025 | 4 | 03-Apr-2025 | 08-Apr-2025 | 4 | 0 | – | High | 35200
T17 | 7.1 | Base Course Laying – Seg B | T16 | Paving Crew | 8 | 09-Apr-2025 | 14-Apr-2025 | 4 | 09-Apr-2025 | 15-Apr-2025 | 5 | 1 | Traffic delay | High | 35200
T18 | 7.2 | Base Course Laying – Seg C | T17 | Paving Crew | 8 | 15-Apr-2025 | 18-Apr-2025 | 4 | 15-Apr-2025 | 22-Apr-2025 | 6 | 2 | Weather + traffic | High | 35200
T19 | 8 | Asphalt Paving – Seg A | T16 | Paving + QC | 10 | 09-Apr-2025 | 11-Apr-2025 | 3 | 09-Apr-2025 | 11-Apr-2025 | 3 | 0 | – | High | 39000
T20 | 8.1 | Asphalt Paving – Seg B | T19 | Paving + QC | 10 | 14-Apr-2025 | 16-Apr-2025 | 3 | 14-Apr-2025 | 17-Apr-2025 | 4 | 1 | Material delay | High | 39000
T21 | 8.2 | Asphalt Paving – Seg C | T20 | Paving + QC | 10 | 17-Apr-2025 | 21-Apr-2025 | 3 | 17-Apr-2025 | 23-Apr-2025 | 5 | 2 | Peak hour shutdown | High | 39000
T22 | 9 | Road Marking & Signage | T21 | Specialist Crew | 5 | 22-Apr-2025 | 24-Apr-2025 | 3 | 22-Apr-2025 | 25-Apr-2025 | 4 | 1 | Permit | Medium | 18000
T23 | 9.1 | Safety Barrier Installation | T22 | General Labour | 6 | 25-Apr-2025 | 25-Apr-2025 | 2 | 25-Apr-2025 | 25-Apr-2025 | 2 | 0 | – | Low | 7800
T24 | 10 | Final Inspection & Handover | T22,T23 | QA/QC Team | 4 | 24-Apr-2025 | 25-Apr-2025 | 2 | 24-Apr-2025 | 25-Apr-2025 | 3 | 1 | Punch-list items | Low | 7600
LEGEND:
Delay > 1 day | Delay = 1 day | On schedule

## Daily Resource Log
DAILY RESOURCE UTILISATION LOG – 8 Weeks (40 Working Days)
Day | Date | Week | Day of Week | Active Tasks | Total Crew (Planned) | Total Crew (Actual) | Crew Util % | Equipment Units | Equipment Util % | Materials Delivered | Delivery Delay? | Idle Hours (crew) | Daily Cost ($)
1 | 03-Mar-2025 | Week 1 | Monday | 1 | 12 | 12 | 100% | 2 | 71% | Yes | No | 0 | 13503
2 | 04-Mar-2025 | Week 1 | Tuesday | 1 | 15 | 14 | 93% | 3 | 91% | Yes | No | 0.9 | 18118
3 | 05-Mar-2025 | Week 1 | Wednesday | 2 | 18 | 18 | 100% | 3 | 71% | Yes | No | 0 | 19452
4 | 06-Mar-2025 | Week 1 | Thursday | 2 | 20 | 20 | 100% | 4 | 71% | Yes | No | 0 | 23932
5 | 07-Mar-2025 | Week 1 | Friday | 3 | 22 | 22 | 100% | 4 | 83% | Yes | No | 0 | 23126
6 | 10-Mar-2025 | Week 2 | Monday | 3 | 20 | 21 | 105% | 4 | 74% | No | No | -2.7 | 23036
7 | 11-Mar-2025 | Week 2 | Tuesday | 4 | 18 | 17 | 94% | 3 | 91% | Yes | No | 0.8 | 18179
8 | 12-Mar-2025 | Week 2 | Wednesday | 4 | 22 | 21 | 95% | 4 | 80% | Yes | No | 1.9 | 24872
9 | 13-Mar-2025 | Week 2 | Thursday | 5 | 24 | 23 | 96% | 4 | 71% | No | No | 2.8 | 25350
10 | 14-Mar-2025 | Week 2 | Friday | 5 | 24 | 22 | 92% | 4 | 78% | Yes | No | 4 | 25464
11 | 17-Mar-2025 | Week 3 | Monday | 5 | 22 | 21 | 95% | 4 | 72% | Yes | No | 2.7 | 23585
12 | 18-Mar-2025 | Week 3 | Tuesday | 5 | 20 | 22 | 110% | 4 | 94% | Yes | No | -1.3 | 24656
13 | 19-Mar-2025 | Week 3 | Wednesday | 5 | 18 | 17 | 94% | 3 | 88% | Yes | No | 1.2 | 18466
14 | 20-Mar-2025 | Week 3 | Thursday | 5 | 22 | 21 | 95% | 4 | 76% | Yes | No | 2.3 | 22692
15 | 21-Mar-2025 | Week 3 | Friday | 5 | 24 | 25 | 104% | 4 | 75% | Yes | No | -2.6 | 25869
16 | 24-Mar-2025 | Week 4 | Monday | 5 | 26 | 26 | 100% | 5 | 78% | Yes | No | 0 | 29028
17 | 25-Mar-2025 | Week 4 | Tuesday | 5 | 26 | 28 | 108% | 5 | 92% | Yes | No | -1.8 | 29231
18 | 26-Mar-2025 | Week 4 | Wednesday | 5 | 24 | 25 | 104% | 4 | 81% | Yes | No | -2 | 26064
19 | 27-Mar-2025 | Week 4 | Thursday | 5 | 22 | 24 | 109% | 4 | 86% | Yes | No | -3.1 | 25370
20 | 28-Mar-2025 | Week 4 | Friday | 5 | 24 | 25 | 104% | 4 | 81% | No | Yes | -2 | 25771
21 | 31-Mar-2025 | Week 5 | Monday | 5 | 26 | 25 | 96% | 5 | 86% | Yes | No | 1.4 | 29394
22 | 01-Apr-2025 | Week 5 | Tuesday | 5 | 28 | 28 | 100% | 5 | 86% | Yes | No | 0 | 29998
23 | 02-Apr-2025 | Week 5 | Wednesday | 5 | 28 | 31 | 111% | 5 | 74% | No | Yes | -8.7 | 31392
24 | 03-Apr-2025 | Week 5 | Thursday | 5 | 26 | 28 | 108% | 5 | 74% | Yes | No | -5.5 | 30829
25 | 04-Apr-2025 | Week 5 | Friday | 5 | 24 | 24 | 100% | 4 | 81% | No | No | 0 | 26766
26 | 07-Apr-2025 | Week 6 | Monday | 5 | 24 | 26 | 108% | 4 | 70% | Yes | No | -6.4 | 28099
27 | 08-Apr-2025 | Week 6 | Tuesday | 5 | 22 | 23 | 105% | 4 | 92% | Yes | No | -0.9 | 24256
28 | 09-Apr-2025 | Week 6 | Wednesday | 5 | 20 | 19 | 95% | 4 | 74% | Yes | No | 2.4 | 22078
29 | 10-Apr-2025 | Week 6 | Thursday | 5 | 18 | 20 | 111% | 3 | 91% | Yes | No | -1.9 | 21122
30 | 11-Apr-2025 | Week 6 | Friday | 5 | 18 | 19 | 106% | 3 | 84% | Yes | No | -1.7 | 19826
31 | 14-Apr-2025 | Week 7 | Monday | 5 | 20 | 19 | 95% | 4 | 75% | Yes | No | 2.4 | 23453
32 | 15-Apr-2025 | Week 7 | Tuesday | 5 | 18 | 17 | 94% | 3 | 71% | Yes | No | 2.8 | 19059
33 | 16-Apr-2025 | Week 7 | Wednesday | 5 | 16 | 15 | 94% | 3 | 77% | Yes | No | 2.2 | 16750
34 | 17-Apr-2025 | Week 7 | Thursday | 5 | 14 | 15 | 107% | 2 | 93% | Yes | No | -0.8 | 15125
35 | 18-Apr-2025 | Week 7 | Friday | 5 | 12 | 12 | 100% | 2 | 97% | Yes | No | 0 | 13585
36 | 21-Apr-2025 | Week 8 | Monday | 5 | 12 | 12 | 100% | 2 | 87% | Yes | No | 0 | 14708
37 | 22-Apr-2025 | Week 8 | Tuesday | 5 | 10 | 11 | 110% | 2 | 89% | Yes | No | -1.2 | 13434
38 | 23-Apr-2025 | Week 8 | Wednesday | 5 | 8 | 9 | 112% | 1 | 88% | No | No | -1.3 | 10449
39 | 24-Apr-2025 | Week 8 | Thursday | 5 | 8 | 7 | 88% | 1 | 76% | Yes | No | 2.1 | 7286
40 | 25-Apr-2025 | Week 8 | Friday | 5 | 6 | 6 | 100% | 1 | 76% | Yes | No | 0 | 6529
TOTALS / AVERAGES |  |  |  | 180 | 781 | 790 | [6 empty] | 869902

## Traffic Patterns
TRAFFIC VOLUME & IMPACT LOG – Hourly Pattern by Day (vehicles/hour and delay index)
Baseline: 2-lane closure active on Arterial Corridor. Peak AM: 07:00–09:00 ¦ Peak PM: 17:00–19:00 ¦ Volumes include construction-related diversions.
Date | Week | Day | Construction Activity | 06:00 | 07:00 | 08:00 | 09:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00 | 15:00 | 16:00 | 17:00 | 18:00 | 19:00 | Daily Total (veh) | Peak Hour Vol (veh/hr) | Delay Index (0–1) | Avg Speed (km/h)
03-Mar-2025 | Week 1 | Monday | Site Mobilisation | 297 | 1325 | 1816 | 1160 | 620 | 750 | 786 | 817 | 659 | 789 | 1070 | 1796 | 1807 | 1348 | 15040 | 1816 | 0.78 | 16.8
04-Mar-2025 | Week 1 | Tuesday | Site Mobilisation | 304 | 1337 | 1944 | 1098 | 853 | 806 | 762 | 762 | 661 | 858 | 977 | 1708 | 2342 | 1385 | 15797 | 2342 | 0.99 | 10
05-Mar-2025 | Week 1 | Wednesday | Site Mobilisation | 365 | 1389 | 1668 | 1284 | 715 | 566 | 794 | 702 | 769 | 846 | 978 | 1923 | 1858 | 1199 | 15056 | 1923 | 0.91 | 10
06-Mar-2025 | Week 1 | Thursday | Site Mobilisation | 324 | 1164 | 2264 | 1010 | 732 | 784 | 680 | 907 | 829 | 760 | 1016 | 1989 | 1607 | 1198 | 15264 | 2264 | 0.99 | 10
07-Mar-2025 | Week 1 | Friday | Site Mobilisation | 321 | 1284 | 1983 | 1186 | 673 | 621 | 740 | 864 | 659 | 779 | 1086 | 1928 | 1617 | 1351 | 15092 | 1983 | 0.97 | 10
10-Mar-2025 | Week 2 | Monday | Utility Relocation + Lane Closure | 380 | 1282 | 2401 | 1362 | 807 | 903 | 983 | 851 | 872 | 1054 | 1146 | 1958 | 2545 | 1478 | 18022 | 2545 | 0.99 | 10
11-Mar-2025 | Week 2 | Tuesday | Utility Relocation + Lane Closure | 373 | 1233 | 2149 | 1443 | 825 | 855 | 874 | 960 | 892 | 822 | 1135 | 2049 | 2149 | 1459 | 17218 | 2149 | 0.99 | 10
12-Mar-2025 | Week 2 | Wednesday | Utility Relocation + Lane Closure | 386 | 1628 | 1837 | 1363 | 829 | 771 | 800 | 862 | 753 | 1050 | 1250 | 1917 | 1830 | 1485 | 16761 | 1917 | 0.9 | 10.3
13-Mar-2025 | Week 2 | Thursday | Utility Relocation + Lane Closure | 343 | 1599 | 2080 | 1228 | 813 | 859 | 842 | 775 | 785 | 915 | 1120 | 1923 | 2057 | 1384 | 16723 | 2080 | 0.99 | 10
14-Mar-2025 | Week 2 | Friday | Utility Relocation + Lane Closure | 328 | 1501 | 1899 | 1370 | 851 | 865 | 947 | 1027 | 885 | 1001 | 1279 | 1883 | 2101 | 1588 | 17525 | 2101 | 0.99 | 10
17-Mar-2025 | Week 3 | Monday | Utility Relocation + Lane Closure | 317 | 1352 | 1947 | 1323 | 783 | 750 | 789 | 971 | 889 | 1048 | 982 | 2024 | 2581 | 1532 | 17288 | 2581 | 0.99 | 10
18-Mar-2025 | Week 3 | Tuesday | Utility Relocation + Lane Closure | 325 | 1321 | 2077 | 1236 | 750 | 713 | 842 | 837 | 761 | 801 | 1004 | 2066 | 2465 | 1277 | 16475 | 2465 | 0.99 | 10
19-Mar-2025 | Week 3 | Wednesday | Utility Relocation + Lane Closure | 400 | 1629 | 2274 | 1412 | 672 | 715 | 820 | 1012 | 789 | 902 | 1307 | 1629 | 2153 | 1614 | 17328 | 2274 | 0.99 | 10
20-Mar-2025 | Week 3 | Thursday | Utility Relocation + Lane Closure | 394 | 1420 | 2307 | 1359 | 844 | 730 | 829 | 1057 | 827 | 1008 | 1157 | 2308 | 2186 | 1495 | 17921 | 2308 | 0.99 | 10
21-Mar-2025 | Week 3 | Friday | Utility Relocation + Lane Closure | 370 | 1467 | 2155 | 1379 | 719 | 775 | 839 | 948 | 843 | 880 | 1047 | 2094 | 2343 | 1573 | 17432 | 2343 | 0.99 | 10
24-Mar-2025 | Week 4 | Monday | Milling + Sub-base | 370 | 1507 | 2067 | 1389 | 816 | 664 | 733 | 973 | 735 | 954 | 1249 | 1734 | 1902 | 1234 | 16327 | 2067 | 0.99 | 10
25-Mar-2025 | Week 4 | Tuesday | Milling + Sub-base | 413 | 1436 | 2264 | 1504 | 799 | 643 | 939 | 971 | 773 | 766 | 1090 | 2054 | 2364 | 1500 | 17516 | 2364 | 0.99 | 10
26-Mar-2025 | Week 4 | Wednesday | Milling + Sub-base | 387 | 1594 | 2194 | 1571 | 715 | 739 | 723 | 801 | 825 | 893 | 1160 | 2266 | 2385 | 1682 | 17935 | 2385 | 0.99 | 10
27-Mar-2025 | Week 4 | Thursday | Milling + Sub-base | 410 | 1461 | 1841 | 1461 | 717 | 826 | 944 | 844 | 738 | 838 | 1095 | 2188 | 2659 | 1474 | 17496 | 2659 | 0.99 | 10
28-Mar-2025 | Week 4 | Friday | Milling + Sub-base | 375 | 1527 | 2186 | 1242 | 759 | 846 | 848 | 946 | 912 | 877 | 1164 | 1954 | 2509 | 1474 | 17619 | 2509 | 0.99 | 10
31-Mar-2025 | Week 5 | Monday | Milling + Sub-base | 399 | 1482 | 2296 | 1394 | 806 | 742 | 791 | 858 | 1013 | 844 | 1204 | 2101 | 2199 | 1570 | 17699 | 2296 | 0.99 | 10
01-Apr-2025 | Week 5 | Tuesday | Milling + Sub-base | 405 | 1744 | 2091 | 1451 | 865 | 694 | 954 | 855 | 823 | 938 | 1066 | 1920 | 2091 | 1435 | 17332 | 2091 | 0.99 | 10
02-Apr-2025 | Week 5 | Wednesday | Milling + Sub-base | 386 | 1647 | 2323 | 1209 | 890 | 820 | 851 | 951 | 814 | 994 | 1112 | 2216 | 2534 | 1389 | 18136 | 2534 | 0.99 | 10
03-Apr-2025 | Week 5 | Thursday | Milling + Sub-base | 365 | 1368 | 2531 | 1420 | 754 | 820 | 961 | 865 | 779 | 846 | 1196 | 1676 | 2427 | 1513 | 17521 | 2531 | 0.99 | 10
04-Apr-2025 | Week 5 | Friday | Milling + Sub-base | 330 | 1394 | 2369 | 1233 | 797 | 775 | 855 | 834 | 795 | 948 | 1199 | 2295 | 2085 | 1631 | 17540 | 2369 | 0.99 | 10
07-Apr-2025 | Week 6 | Monday | Paving | 395 | 1497 | 2073 | 1439 | 884 | 841 | 947 | 916 | 841 | 894 | 1111 | 1699 | 2410 | 1625 | 17572 | 2410 | 0.99 | 10
08-Apr-2025 | Week 6 | Tuesday | Paving | 395 | 1677 | 1844 | 1398 | 967 | 876 | 1004 | 938 | 747 | 939 | 1180 | 2344 | 1862 | 1422 | 17593 | 2344 | 0.99 | 10
09-Apr-2025 | Week 6 | Wednesday | Paving | 314 | 1737 | 1948 | 1357 | 774 | 738 | 772 | 1001 | 916 | 908 | 1009 | 1951 | 2178 | 1423 | 17026 | 2178 | 0.99 | 10
10-Apr-2025 | Week 6 | Thursday | Paving | 344 | 1651 | 1971 | 1160 | 874 | 812 | 793 | 934 | 774 | 865 | 981 | 2094 | 2156 | 1406 | 16815 | 2156 | 0.99 | 10
11-Apr-2025 | Week 6 | Friday | Paving | 324 | 1392 | 1952 | 1227 | 686 | 809 | 899 | 983 | 762 | 929 | 1275 | 1987 | 2198 | 1449 | 16872 | 2198 | 0.99 | 10
14-Apr-2025 | Week 7 | Monday | Paving | 371 | 1367 | 1780 | 1417 | 853 | 760 | 808 | 1028 | 915 | 915 | 1046 | 1898 | 1953 | 1510 | 16621 | 1953 | 0.91 | 10
15-Apr-2025 | Week 7 | Tuesday | Paving | 371 | 1470 | 1976 | 1478 | 840 | 678 | 849 | 1042 | 963 | 914 | 1074 | 1951 | 2111 | 1517 | 17234 | 2111 | 0.99 | 10
16-Apr-2025 | Week 7 | Wednesday | Paving | 434 | 1637 | 1944 | 1602 | 722 | 769 | 743 | 1013 | 764 | 863 | 1117 | 1891 | 2204 | 1607 | 17310 | 2204 | 0.99 | 10
17-Apr-2025 | Week 7 | Thursday | Paving | 345 | 1475 | 2159 | 1278 | 800 | 718 | 887 | 873 | 834 | 780 | 967 | 1810 | 2016 | 1337 | 16279 | 2159 | 0.99 | 10
18-Apr-2025 | Week 7 | Friday | Paving | 420 | 1433 | 1671 | 1609 | 840 | 787 | 704 | 931 | 918 | 932 | 1149 | 2046 | 2037 | 1380 | 16857 | 2046 | 0.97 | 10
21-Apr-2025 | Week 8 | Monday | Finishing + Handover | 294 | 1391 | 2062 | 1216 | 618 | 720 | 731 | 860 | 823 | 863 | 1023 | 1943 | 1830 | 1158 | 15532 | 2062 | 0.99 | 10
22-Apr-2025 | Week 8 | Tuesday | Finishing + Handover | 289 | 1236 | 1752 | 1156 | 794 | 666 | 803 | 877 | 817 | 770 | 824 | 1719 | 1924 | 1221 | 14848 | 1924 | 0.87 | 11.8
23-Apr-2025 | Week 8 | Wednesday | Finishing + Handover | 320 | 1169 | 1706 | 1173 | 787 | 554 | 751 | 877 | 869 | 788 | 872 | 2032 | 1901 | 1388 | 15187 | 2032 | 0.97 | 10
24-Apr-2025 | Week 8 | Thursday | Finishing + Handover | 359 | 1481 | 1926 | 1219 | 674 | 585 | 829 | 703 | 708 | 769 | 1138 | 1507 | 1881 | 1181 | 14960 | 1926 | 0.92 | 11
25-Apr-2025 | Week 8 | Friday | Finishing + Handover | 325 | 1265 | 1808 | 1128 | 751 | 651 | 802 | 852 | 894 | 768 | 959 | 2079 | 1899 | 1265 | 15446 | 2079 | 0.99 | 10
WEEKLY TRAFFIC SUMMARY
Week | Dates | Avg Daily Vol (veh/day) | Peak Vol (veh/hr) | Avg Delay Index | Avg Speed (km/h) | Construction Phase | Notable Events
Week 1 | 03–07 Mar | 9,450 | 1,245 | 0.32 | 48 | Site Mobilisation | Minor disruption; traffic management beginning
Week 2 | 10–14 Mar | 11,200 | 1,380 | 0.44 | 39 | Utility Relocation | Gas line work causes 1-hour shutdowns; detours active
Week 3 | 17–21 Mar | 13,500 | 1,510 | 0.58 | 31 | Lane Closure + Milling | 2-lane closure; peak AM severely congested
Week 4 | 24–28 Mar | 14,200 | 1,620 | 0.66 | 26 | Milling + Sub-base | Worst congestion week; weather event Day 18
Week 5 | 31 Mar–04 Apr | 12,800 | 1,490 | 0.55 | 33 | Sub-base + Drainage | Moderate; rain delay adds cascade effect
Week 6 | 07–11 Apr | 12,100 | 1,420 | 0.50 | 36 | Drainage + Base Paving | Recovery; one equipment breakdown
Week 7 | 14–18 Apr | 10,800 | 1,320 | 0.42 | 41 | Asphalt Paving | Lane partially reopened mid-week; traffic easing
Week 8 | 22–26 Apr | 8,600 | 1,180 | 0.28 | 51 | Finishing + Handover | Near-normal; final marking & inspection

## Cost Tracking
COST TRACKING LEDGER – Planned vs Actual with Variance Analysis
Week | Task ID | Cost Category | Planned Cost ($) | Actual Cost ($) | Variance ($) | Variance % | Cause of Overrun | Delay-linked? | Cumulative Actual ($)
Week 1 | T10 | Labour | 10625 | 10530 | -95 | -0.8941% | Material cost increase | Yes | 10530
Week 1 | T09 | Equipment Hire | 8125 | 7991 | -134 | -1.649% | Labour overtime | Yes | 18521
Week 1 | T14 | Materials | 6875 | 7767 | 892 | 12.97% | Labour overtime | Yes | 26288
Week 1 | T15 | Traffic Management | 1875 | 1850 | -25 | -1.333% | Equipment breakdown | Yes | 28138
Week 1 | T14 | Subcontractor | 3750 | 4889 | 1139 | 30.37% | Traffic delay | Yes | 33027
Week 1 | T08 | QA/QC | 1000 | 971 | -29 | -2.9% | On budget | No | 33998
Week 1 | T12 | Site Overheads | 1500 | 1657 | 157 | 10.47% | Material cost increase | Yes | 35655
Week 1 | T04 | Contingency Draw | 0 | 0 | 0 | 0% | On budget | No | 35655
Week 2 | T05 | Labour | 11688 | 15027 | 3339 | 28.57% | On budget | No | 50682
Week 2 | T16 | Equipment Hire | 8938 | 8983 | 45 | 0.5035% | Weather | Yes | 59665
Week 2 | T23 | Materials | 7563 | 9291 | 1728 | 22.85% | Labour overtime | Yes | 68956
Week 2 | T03 | Traffic Management | 2062 | 2346 | 284 | 13.77% | Traffic delay | Yes | 71302
Week 2 | T05 | Subcontractor | 4125 | 3950 | -175 | -4.242% | Equipment breakdown | Yes | 75252
Week 2 | T04 | QA/QC | 1100 | 1286 | 186 | 16.91% | – | No | 76538
Week 2 | T10 | Site Overheads | 1650 | 2080 | 430 | 26.06% | Equipment breakdown | Yes | 78618
Week 2 | T14 | Contingency Draw | 0 | 0 | 0 | 0% | Equipment breakdown | Yes | 78618
Week 3 | T03 | Labour | 12750 | 15371 | 2621 | 20.56% | – | No | 93989
Week 3 | T20 | Equipment Hire | 9750 | 9695 | -55 | -0.5641% | – | No | 103684
Week 3 | T23 | Materials | 8250 | 9606 | 1356 | 16.44% | Equipment breakdown | Yes | 113290
Week 3 | T01 | Traffic Management | 2250 | 2267 | 17 | 0.7556% | – | No | 115557
Week 3 | T19 | Subcontractor | 4500 | 5382 | 882 | 19.6% | Equipment breakdown | Yes | 120939
Week 3 | T17 | QA/QC | 1200 | 1340 | 140 | 11.67% | Material cost increase | Yes | 122279
Week 3 | T17 | Site Overheads | 1800 | 2412 | 612 | 34% | Material cost increase | Yes | 124691
Week 3 | T13 | Contingency Draw | 0 | 0 | 0 | 0% | Traffic delay | Yes | 124691
Week 4 | T21 | Labour | 13812 | 17946 | 4134 | 29.93% | Traffic delay | Yes | 142637
Week 4 | T09 | Equipment Hire | 10562 | 11668 | 1106 | 10.47% | On budget | No | 154305
Week 4 | T03 | Materials | 8938 | 11163 | 2225 | 24.89% | On budget | No | 165468
Week 4 | T19 | Traffic Management | 2438 | 2652 | 214 | 8.778% | Material cost increase | Yes | 168120
Week 4 | T05 | Subcontractor | 4875 | 6065 | 1190 | 24.41% | On budget | No | 174185
Week 4 | T21 | QA/QC | 1300 | 1258 | -42 | -3.231% | On budget | No | 175443
Week 4 | T23 | Site Overheads | 1950 | 1989 | 39 | 2% | – | No | 177432
Week 4 | T05 | Contingency Draw | 0 | 0 | 0 | 0% | Labour overtime | Yes | 177432
Week 5 | T02 | Labour | 12219 | 11916 | -303 | -2.48% | – | No | 189348
Week 5 | T07 | Equipment Hire | 9344 | 9974 | 630 | 6.742% | Traffic delay | Yes | 199322
Week 5 | T10 | Materials | 7906 | 10312 | 2406 | 30.43% | On budget | No | 209634
Week 5 | T09 | Traffic Management | 2156 | 2493 | 337 | 15.63% | – | No | 212127
Week 5 | T10 | Subcontractor | 4312 | 4160 | -152 | -3.525% | Equipment breakdown | Yes | 216287
Week 5 | T21 | QA/QC | 1150 | 1257 | 107 | 9.304% | Traffic delay | Yes | 217544
Week 5 | T12 | Site Overheads | 1725 | 1868 | 143 | 8.29% | Material cost increase | Yes | 219412
Week 5 | T24 | Contingency Draw | 0 | 0 | 0 | 0% | – | No | 219412
Week 6 | T11 | Labour | 11156 | 12560 | 1404 | 12.59% | – | No | 231972
Week 6 | T23 | Equipment Hire | 8531 | 11427 | 2896 | 33.95% | – | No | 243399
Week 6 | T03 | Materials | 7219 | 8295 | 1076 | 14.91% | Weather | Yes | 251694
Week 6 | T14 | Traffic Management | 1969 | 2443 | 474 | 24.07% | Material cost increase | Yes | 254137
Week 6 | T18 | Subcontractor | 3938 | 4690 | 752 | 19.1% | Labour overtime | Yes | 258827
Week 6 | T03 | QA/QC | 1050 | 1121 | 71 | 6.762% | Material cost increase | Yes | 259948
Week 6 | T10 | Site Overheads | 1575 | 1703 | 128 | 8.127% | Weather | Yes | 261651
Week 6 | T06 | Contingency Draw | 0 | 0 | 0 | 0% | – | No | 261651
Week 7 | T15 | Labour | 10625 | 13025 | 2400 | 22.59% | On budget | No | 274676
Week 7 | T20 | Equipment Hire | 8125 | 7856 | -269 | -3.311% | On budget | No | 282532
Week 7 | T21 | Materials | 6875 | 9276 | 2401 | 34.92% | Weather | Yes | 291808
Week 7 | T03 | Traffic Management | 1875 | 2516 | 641 | 34.19% | Traffic delay | Yes | 294324
Week 7 | T12 | Subcontractor | 3750 | 4569 | 819 | 21.84% | – | No | 298893
Week 7 | T01 | QA/QC | 1000 | 1155 | 155 | 15.5% | Labour overtime | Yes | 300048
Week 7 | T02 | Site Overheads | 1500 | 1511 | 11 | 0.7333% | – | No | 301559
Week 7 | T21 | Contingency Draw | 0 | 0 | 0 | 0% | Equipment breakdown | Yes | 301559
Week 8 | T19 | Labour | 8500 | 9321 | 821 | 9.659% | – | No | 310880
Week 8 | T22 | Equipment Hire | 6500 | 6259 | -241 | -3.708% | Labour overtime | Yes | 317139
Week 8 | T12 | Materials | 5500 | 6215 | 715 | 13% | On budget | No | 323354
Week 8 | T19 | Traffic Management | 1500 | 1691 | 191 | 12.73% | Material cost increase | Yes | 325045
Week 8 | T13 | Subcontractor | 3000 | 3015 | 15 | 0.5% | On budget | No | 328060
Week 8 | T08 | QA/QC | 800 | 861 | 61 | 7.625% | Weather | Yes | 328921
Week 8 | T24 | Site Overheads | 1200 | 1601 | 401 | 33.42% | Traffic delay | Yes | 330522
Week 8 | T18 | Contingency Draw | 0 | 0 | 0 | 0% | – | No | 330522
PROJECT TOTALS |  |  | 290251 | 330522 | 40271

## Risk & Uncertainty Log
RISK REGISTER & UNCERTAINTY EVENT LOG – Observed Events for Monte Carlo Calibration
Event ID | Date | Week | Risk Category | Description | Probability (assigned) | Occurred? | Impact Type | Delay Caused (days) | Cost Impact ($) | Affected Tasks
R001 | 05-Mar-2025 | Wk1 | Traffic | Peak-hour delivery truck blocked site access | 0.30 | Yes | Schedule+Cost | 1 | 8500 | T02,T05
R002 | 07-Mar-2025 | Wk1 | Permit | Lane closure permit delayed by city authority | 0.20 | Yes | Schedule | 1 | 4200 | T05,T06
R003 | 11-Mar-2025 | Wk2 | Material | Gas pipe fittings delivered wrong spec | 0.15 | Yes | Schedule+Cost | 2 | 18000 | T03
R004 | 12-Mar-2025 | Wk2 | Traffic | AM peak congestion caused equipment standby (2 hrs) | 0.40 | Yes | Cost | 0 | 7000 | T06,T07
R005 | 14-Mar-2025 | Wk2 | Equipment | Milling machine hydraulic failure – 4hr downtime | 0.05 | Yes | Schedule+Cost | 1 | 12000 | T07
R006 | 17-Mar-2025 | Wk3 | Traffic | Road diversion route overloaded; nearby signal failed | 0.25 | Yes | Traffic+Cost | 0 | 3500 | T05,T06
R007 | 19-Mar-2025 | Wk3 | Weather | Rainfall halted paving for 1.5 days | 0.08 | Yes | Schedule | 2 | 9000 | T09,T10
R008 | 20-Mar-2025 | Wk3 | Labour | Crew absenteeism (illness) – 4 workers day off | 0.12 | Yes | Schedule | 0 | 6000 | T10
R009 | 24-Mar-2025 | Wk4 | Traffic | Peak conflict – city event; corridor volume +45% | 0.10 | Yes | Traffic+Schedule | 1 | 11000 | T06,T13
R010 | 25-Mar-2025 | Wk4 | Material | Aggregate delivery 1 day late (supplier OOS) | 0.20 | Yes | Schedule | 1 | 4500 | T11,T12
R011 | 26-Mar-2025 | Wk4 | Weather | Heavy wind; crane ops suspended for 3 hrs | 0.05 | Yes | Cost | 0 | 5500 | T13
R012 | 28-Mar-2025 | Wk4 | Traffic | AM peak 90-min blockage due to accident upstream | 0.15 | Yes | Traffic | 0 | 2800 | T07,T08
R013 | 03-Apr-2025 | Wk5 | Equipment | Compactor breakdown – 6 hrs repair | 0.05 | Yes | Schedule+Cost | 1 | 14000 | T15
R014 | 04-Apr-2025 | Wk5 | Traffic | Friday PM peak exceeded model by 28% | 0.30 | Yes | Traffic | 0 | 1500 | T16
R015 | 07-Apr-2025 | Wk6 | Material | Asphalt batch rejected by QC – reorder required | 0.10 | Yes | Schedule+Cost | 2 | 22000 | T19,T20
R016 | 09-Apr-2025 | Wk6 | Labour | Subcontractor dispute – 2hr work stoppage | 0.08 | Yes | Schedule | 0 | 8000 | T14
R017 | 11-Apr-2025 | Wk6 | Traffic | Lane reopen partial – traffic rerouting confusion | 0.20 | No | – | 0 | 0 | –
R018 | 14-Apr-2025 | Wk7 | Weather | Light rain – asphalt paving delayed 4 hrs | 0.08 | Yes | Schedule | 1 | 7500 | T21
R019 | 16-Apr-2025 | Wk7 | Traffic | Peak PM shutdown required by traffic police | 0.15 | Yes | Schedule+Cost | 1 | 9500 | T21
R020 | 18-Apr-2025 | Wk7 | Permit | Road marking permit clarification – 2hr delay | 0.10 | Yes | Schedule | 0 | 2000 | T22
R021 | 22-Apr-2025 | Wk8 | QA | Punch-list: 3 defects in road marking quality | 0.15 | Yes | Schedule | 1 | 5000 | T22,T24
R022 | 23-Apr-2025 | Wk8 | Traffic | Final inspection day – minor access conflict | 0.10 | No | – | 0 | 0 | T24

## Traffic – Optimisation Input
TRAFFIC PATTERN MATRIX – Structured Input for Scheduling Optimisation Model
Key parameters: Delay Multiplier (DM) applied to task durations when scheduled during peak windows. Peak AM = 07:00–09:00 ¦ Peak PM = 17:00–19:00 ¦ Off-peak DM = 1.0 baseline
Time Slot | Hour Range | Monday | Tuesday | Wednesday | Thursday | Friday | Avg DM | Recommended Work Window?
Early Morning | 05:00–07:00 | 1 | 1 | 1 | 1 | 1 | 1 | Preferred
AM Peak | 07:00–09:00 | 1.72 | 1.65 | 1.68 | 1.7 | 1.6 | 1.67 | AVOID
AM Shoulder | 09:00–10:00 | 1.25 | 1.2 | 1.22 | 1.24 | 1.18 | 1.22 | Caution
Midday | 10:00–12:00 | 1.08 | 1.05 | 1.06 | 1.07 | 1.05 | 1.06 | OK
Lunch Peak | 12:00–13:00 | 1.18 | 1.15 | 1.2 | 1.16 | 1.14 | 1.17 | Caution
Afternoon | 13:00–16:00 | 1.1 | 1.08 | 1.09 | 1.1 | 1.07 | 1.09 | OK
PM Shoulder | 16:00–17:00 | 1.32 | 1.28 | 1.3 | 1.31 | 1.25 | 1.29 | Caution
PM Peak | 17:00–19:00 | 1.75 | 1.7 | 1.68 | 1.72 | 1.8 | 1.73 | AVOID
Evening | 19:00–21:00 | 1.05 | 1.03 | 1.04 | 1.03 | 1.02 | 1.03 | OK
Night | 21:00–05:00 | 1 | 1 | 1 | 1 | 1 | 1 | Preferred
INTERPRETATION: Delay Multiplier (DM) = ratio of actual task duration to planned when scheduled in this time window. DM > 1.5 = HIGH RISK ¦ 1.2–1.5 = MODERATE ¦ < 1.2 = LOW. Use in optimisation as: actual_duration = planned_duration × DM(time_slot).